## Bright Coffee shop
| BRIGHT COFFEE SHOP | [5 empty] | Project start: | [7 empty] | 2026-03-15
[7 empty] | Display week: | [7 empty] | 1899-12-31
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-03-16 to 2026-05-10
 | time axis 2026-03-16 to 2026-05-10
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
PLANNING
| Data flow chart | Lungile Chirwa | 100% | 2026-03-15 | 2026-03-17 | 3
| Proposal and feedback | Lungile Chirwa | 100% | 2026-03-17 | 2026-03-19 | 3
DATA PROCESSING
| Convert Excel to CSV file | Lungile Chirwa | 100% | 2026-03-18 | 2026-03-20 | 3
| Load data into databricks | Lungile Chirwa | 100% | 2026-03-18 | 2026-03-20 | 3
| SQL Transformation and cleaning | Lungile Chirwa | 100% | 2026-03-20 | 2026-03-21 | 2
| Create time buckets and calculate fied | Lungile Chirwa | 100% | 2026-03-20 | 2026-03-22 | 3
DATA ANALYSIS
| Export Processed data to excel | Lungile Chirwa | 100% | 2026-03-23 | 2026-03-24 | 2
| Create Pivot Tables | Lungile Chirwa | 100% | 2026-03-24 | 2026-03-25 | 2
| Build charts and dashboard | Lungile Chirwa | 100% | 2026-03-24 | 2026-03-26 | 3
| insights | Lungile Chirwa | 100% | 2026-03-24 | 2026-03-26 | 3
| Testing and validation | Lungile Chirwa | 100% | 2026-03-24 | 2026-03-26 | 3
PRESENTATION AND SUBMISSION
| Draft PowerPoint presentation | Lungile Chirwa | 100% | 2026-03-26 | 2026-03-29 | 4
| Final review & polish | Lungile Chirwa | 100% | 2026-03-26 | 2026-03-29 | 4
| SUBMISSION | Lungile Chirwa | 100% | 2026-03-26 | 2026-03-29 | 4